## Summary Dashboard
Safe By Design Maturity Assessment Summary Report
Date Completed:
Reviewer(s)
|  | Assessment Status |  | Maturity Level
Overall Level |  | 0% | 0 | 0% | 0%
1 | Generic Safe By Design Requirements | 0% | 0% | 0% | 0%
1.1 | Risk Management and Hazard Reviews | 0% | 0 | 0% | 0
1.2 | Hierarchy of Controls | 0% | 0 | 0% | 0
1.3 | Decision Making | 0% | 0 | 0% | 0
1.4 | Asset Information Management | 0% | 0 | 0% | 0
1.5 | Safety Culture | 0% | 0 | 0% | 0
1.6 | Assurance | 0% | 0 | 0% | 0
1.7 | Management of Procured Equipment and Outsourced Activities | 0% | 0 | 0% | 0
1.8 | Adoption of New Technologies | 0% | 0 | 0% | 0
2 | Development Phase | 0% | 0% | 0% | 0%
2.1 | Project Health and Safety plan | 0% | 0 | 0% | 0
2.2 | Structured Approach to Early Design | 0% | 0 | 0% | 0
2.3 | Operations and Maintenance Philosophy | 0% | 0 | 0% | 0
2.4 | Decommissioning | 0% | 0 | 0% | 0
2.5 | Lessons Learned | 0% | 0 | 0% | 0
3 | Detailed Design | 0% | 0% | 0% | 0%
3.1 | Design Basis | 0% | 0 | 0% | 0
3.2 | Interface Management | 0% | 0 | 0% | 0
3.3 | Management of Degradation and Deterioration | 0% | 0 | 0% | 0
3.4 | Design for Constructability, Operability, Maintainability and Decommissioning | 0% | 0 | 0% | 0
3.5 | Design for Escape and Evacuation | 0% | 0 | 0% | 0
3.6 | Safety Critical Systems | 0% | 0 | 0% | 0
3.7 | Design Freeze and Design Change Management | 0% | 0 | 0% | 0
3.8 | Design Reviews | 0% | 0 | 0% | 0
3.9 | Design Verification and Design Assurance | 0% | 0 | 0% | 0
4 | Construction | 0% | 0% | 0% | 0%
4.1 | Work Scheduling | 0% | 0 | 0% | 0
4.2 | Management of Temporary Works | 0% | 0 | 0% | 0
4.3 | Quality Management | 0% | 0 | 0% | 0
4.4 | Design Change | 0% | 0 | 0% | 0
4.5 | Capturing Lessons Learned | 0% | 0 | 0% | 0
5 | Asset Adoption | 0% | 0% | 0% | 0%
5.1 | Handover | 0% | 0 | 0% | 0
5.2 | Conversation of Design Information into Operations Documents | 0% | 0 | 0% | 0
6 | Operations | 0% | 0% | 0% | 0%
6.1 | Design Validation | 0% | 0 | 0% | 0
6.2 | Maintaining H&S objectives | 0% | 0 | 0% | 0
6.3 | Emergency Response | 0% | 0 | 0% | 0
6.4 | Inspection, Maintenance and Monitoring | 0% | 0 | 0% | 0
6.5 | Asset Modifications and Brownfield projects | 0% | 0 | 0% | 0
6.6 | Capturing Operational Experience | 0% | 0 | 0% | 0
6.7 | Life Extension | 0% | 0 | 0% | 0
6.8 | Decommissioning Plan Review | 0% | 0 | 0% | 0
7 | Decommissioning | 0% | 0% | 0% | 0%
7.1 | Planning | 0% | 0 | 0% | 0
7.2 | Degradation Assessment | 0% | 0 | 0% | 0
Note on F7: G+: This will be automatically updated by the values set in the 'Status' columns in sheets 1 to 7

## 1. Generic Requirements
1. Generic requirements
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
1.1 | Risk Management and Hazard Reviews
1.1.1 | Is there a systematic approach to hazard identification, prevention and mitigation throughout the organisation? |  |  |  | Not Assessed
1.1.2 | Is there a continuous process of hazard reviews taking place at appropriate times in the project and asset lifecycle? |  |  |  | Not Assessed
1.1.3 | Do hazard reviews include input from a suitable range of stakeholders, including operational personnel and H&S specialists, with sufficient competence to assess the full range of hazards? |  |  |  | Not Assessed
1.1.4 | Where multiple hazards reviews are carried out, is there a process to ensure they collectively cover all hazards, and the interrelationship between risk reduction measures are understood and managed? |  |  |  | Not Assessed
1.1.5 | Are hazard reviews a key part of a project schedule and do they link to formal project gateways? |  |  |  | Not Assessed
1.1.6 | Are equipment suppliers or entities delivering outsourced activities required to carryout hazard reviews? |  |  |  | Not Assessed
1.1.7 | Where it is necessary to conduct further analysis to fully assess risk levels can it be demonstrated that this is suitable and proportionate to the hazard? |  |  |  | Not Assessed
1.1.8 | Are hazard reviews recorded including output, scope and attendees? |  |  |  | Not Assessed
1.1.9 | Can it be demonstrated that proportionate and suitable risk reduction measures and good industry practice are applied? |  |  |  | Not Assessed
1.1.10 | Is there a process to ensure that necessary further risk reduction measures are planned, allocated sufficient resource and their implementation monitored? |  |  |  | Not Assessed
1.1.11 | Is there a process to ensure that decisions to not implement available risk reduction measures, because they are considered to be grossly disproportionate, justified and documented? |  |  |  | Not Assessed
1.1.12 | Are hazards that will be influenced by equipment suppliers or via outsourced activities identified, recorded and used to develop an appropriate management plans? |  |  |  | Not Assessed
1.1.13 | Is there a demonstrable link between the output of the hazard reviews and the risk management activities in the design process, and the design decision log? |  |  |  | Not Assessed
1.1.14 | Are there activities to understand relevant good industry practice, and is this adhered to unless there is clear justification to deviate? |  |  |  | Not Assessed
1.1.15 | Is the effectiveness of risk reduction measures assessed and, where appropriate, consideration given to implementing further measures? |  |  |  | Not Assessed
1.1.16 | When emergency response / emergency evacuation is a stated risk reduction measure does the hazard review include an assessment of the rate of escalation to understand how quickly it would need to be enacted in real world situations? |  |  |  | Not Assessed
1.1.17 | Are residual risks (i.e., those that are considered to be acceptable) clearly recorded in a risk register, which clearly states which phase(s) they may manifest and the assumptions the assessment is based upon? |  |  |  | Not Assessed
1.1.18 | Are there activities to monitor the continued application of the risk reduction measures to ensure their ongoing effectiveness, identify whether the risk level has increased, and the basis for the prior evaluation has not changed? |  |  |  | Not Assessed
1.1.19 | Is residual risk information and risk reduction measures transferred to relevant stakeholders through the life-cycle? |  |  |  | Not Assessed
1.2 | Hierarchy of Controls
1.2.1 | Is the Hierarchy of Control concept used when making decisions regarding risk management and the selection of suitable risk reduction measures? |  |  |  | Not Assessed
1.3 | Decision Making
1.3.1 | Is there a structured process for decisions related to health and safety? |  |  |  | Not Assessed
1.3.2 | Is there oversight for critical health and safety decisions that considers the complexity of the decision, uniqueness of the decision, worst-case consequence if there is an error in decision making, extent good industry practice can be used to support the decision, level of uncertainty in the input information and analysis, and the number of stakeholders effected? |  |  |  | Not Assessed
1.3.3 | Does the decision making process relating to health and safety account for human factors, which can be a source of error, and are steps taken to minimise the risk of adverse outcomes? |  |  |  | Not Assessed
1.3.4 | Where possible are decisions relating to health and safety fact-based and data driven? |  |  |  | Not Assessed
1.3.5 | Do decision support tools relating to health and safety have an owner who is responsible for ensuring that it is suitable, the outputs are valid and consistent, there is appropriate quality control, it is used consistently, implemented effectively, changes are appropriately managed and there is a feedback loop that includes an assessment of the outcomes? |  |  |  | Not Assessed
1.3.6 | Where appropriate are decisions relating to health and safety codified into an organisation’s management system and technical specifications? Where this approach is taken is there a clear scope that describes the applicability and any limitations and constraints? |  |  |  | Not Assessed
1.3.7 | Is there appropriate rigor and assurance including peer reviews, impact assessment and implementation plans for new specifications and processes relating to health and safety? |  |  |  | Not Assessed
1.3.8 | Are specifications and processes relating to health and safety subject to version control and change management? |  |  |  | Not Assessed
1.4 | Asset Information Management
1.4.1 | Is an asset information strategy that provides a ‘single source of truth’ and includes the information requirements necessary to safely manage the asset? |  |  |  | Not Assessed
1.4.2 | Is a philosophy of ‘right information, to the right people, at right time’ adopted and can this be demonstrated? |  |  |  | Not Assessed
1.4.3 | Are there activities to identify and understand the information that may be required to effectively manage health and safety risks throughout an asset's lifecycle? |  |  |  | Not Assessed
1.4.4 | Is asset information maintained and updated where necessary including hazard and risk registers, assumptions design decision log, design information, as built records, O&M manuals, modification register, and an asset register? |  |  |  | Not Assessed
1.4.5 | Do relevant stakeholders have access to the necessary information and is this managed through a document management system? |  |  |  | Not Assessed
1.5 | Safety Culture
1.5.1 | Is there a programme or initiative to establish the right organisational culture for effective management of health and safety? |  |  |  | Not Assessed
1.5.2 | Are there activities to: • Establish shared values by communicating the safety and environmental objectives, • Ensure engagement and involvement from all organisational levels, • Include contracting organisations within initiatives and reviews, • Provide transparency in process and decisions, • Enable freedom to challenge and provide alternative viewpoints, • Promote continuous improvement? |  |  |  | Not Assessed
1.5.3 | Is an environment that supports effective teamwork, collaboration, and challenge promoted? |  |  |  | Not Assessed
1.6 | Assurance
1.6.1 | Are quality plans implemented that are risk-based considering the hazards and health and safety risks? |  |  |  | Not Assessed
1.6.2 | Is there a demonstrable alignment between the hazards and risk reduction measures, and the activities included in the inspection and surveillance plan? |  |  |  | Not Assessed
1.6.3 | Is there a design assurance programme that is included in the project reporting process, and does this include leading and lagging indicators that are appropriate for each phase of the project? |  |  |  | Not Assessed
1.7 | Management of Procured Equipment and Outsourced Activities
1.7.1 | Are appropriate controls implemented for procured equipment and outsourced activities to ensure they conform to health and safety objectives? |  |  |  | Not Assessed
1.7.2 | Are there processes to ensure there is sufficient assurance and oversight in place for procured equipment and outsourced activities? |  |  |  | Not Assessed
1.7.3 | Is consideration given to the extent prescriptive requirements can be applied at interfaces between contracts? |  |  |  | Not Assessed
1.7.4 | Can it be demonstrated that the compatibility between different suppliers’ equipment and design is assessed to ensure no unacceptable risks emerge at the interfaces? |  |  |  | Not Assessed
1.7.5 | Can be demonstrated that appropriate approval and sign-off gateways are identified to provide the necessary oversight and control, and that these are outlined within contracts? |  |  |  | Not Assessed
1.7.6 | Are there processes to ensure that procured equipment has been designed and evaluated using appropriate and structured design risk assessment processes, and there are mechanisms in the specifications to ensure suitable risk reduction measures are implemented? |  |  |  | Not Assessed
1.7.7 | Are there technical due diligence assessments to evaluate procured equipment against health and safety requirements, including: • Ability to adequately isolate any stored energy from the system • Guarding • Hazards and associated risk reduction measures relating to routine maintenance • Hazards and associated risk reduction measures relating to non-routine maintenance • Health, Safety and Environmental Hazards during manufacturing processes • H&S Hazards during build/installation • Recyclability of the asset components • Lessons learned • Performance guarantees • Decommissioning implications • Sustainability of equipment |  |  |  | Not Assessed
1.7.8 | Is there a process to ensure that design decisions made by equipment suppliers and external designers that have an impact on health and safety are subject to a design risk assessment and require review and approval? |  |  |  | Not Assessed
1.7.9 | Is there are process to ensure that specifications are produced with an objective of achieving good safe by design outcomes? |  |  |  | Not Assessed
1.7.10 | Are the safety goals and requirements clearly defined at the project level and cascaded into the supply chain? |  |  |  | Not Assessed
1.8 | Adoption of New Technologies
1.8.1 | Is there a process for assessing the maturity of the technology alongside the associated health and safety risks? |  |  |  | Not Assessed
1.8.2 | When assessing new technology, are conditions for testing the prototypes compared with the expected operational criteria to assess applicability? |  |  |  | Not Assessed
1.8.3 | Are non-routine activities that could result from unproven technology and introduce significant hazards considered and appropriate mitigations implemented? |  |  |  | Not Assessed
1.8.4 | Are there specific activities to identify any systemisation risks and appropriate controls implemented? |  |  |  | Not Assessed
1.8.5 | Are changes to existing operational processes and competency requirements due to new technology assessed and appropriate change management implemented? |  |  |  | Not Assessed
Note on C2: G+: Use the No, Partially, Yes columns when working on a hard copy
Note on F2: G+: Use this column to set the value and automatically populate the 'Summary Dashboard' sheet

## 2. Development
2. Development Phase
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
2.1 | Project Health and Safety plan
2.1.1 | Is a health and safety plan produced in the development phase? |  |  |  | Not Assessed
2.1.2 | Does the health and safety plan identify key risks for the construction, operations and decommissioning phases? Does this include, for example, the expected deployment of new technology, weather or environmental factors, or issues relating to the site location? |  |  |  | Not Assessed
2.1.3 | Does the health and safety plan set out how hazard reviews will be used to support decision making? |  |  |  | Not Assessed
2.1.4 | Does the health and safety plan set out how residual risks will be made visible to relevant stakeholders and considered during design reviews and project approval gateways? |  |  |  | Not Assessed
2.1.5 | Does the health and safety plan set out how Safe By Design will be part of the project monitoring and reporting processes with appropriate leading and lagging indicators? |  |  |  | Not Assessed
2.1.6 | Does the health and safety plan set out how there will be suitable competency levels with respect to Safe By Design? |  |  |  | Not Assessed
2.1.7 | Does the health and safety plan set out how risk assessment tools will be adopted and the outputs used directly in the design process? |  |  |  | Not Assessed
2.1.8 | Does the health and safety plan outline initial assumptions for logistics, access and egress and emergency response? |  |  |  | Not Assessed
2.2 | Structured Approach to Early Design
2.2.1 | Is there are structured approach to early design? |  |  |  | Not Assessed
2.2.2 | Are early design scenarios, analysis, modelling and options reviewed and compared against health and safety criteria? |  |  |  | Not Assessed
2.3 | Operations and Maintenance Philosophy
2.3.1 | Is an operations and maintenance philosophy produced in the development phase? |  |  |  | Not Assessed
2.3.2 | Does an operations and maintenance philosophy in the development phase establish, record and communicate the long-term vision of the operational phase of the project? |  |  |  | Not Assessed
2.3.4 | Does an operations and maintenance philosophy in the development phase include anticipated maintenance strategies? |  |  |  | Not Assessed
2.3.5 | Does an operations and maintenance philosophy in the development phase include a logistics plan covering how material will be transported to the point of work? |  |  |  | Not Assessed
2.3.6 | Does an operations and maintenance philosophy in the development phase include a strategy for the management of fire risks? |  |  |  | Not Assessed
2.3.7 | Does the operations and maintenance philosophy include an initial emergency response plan? |  |  |  | Not Assessed
2.3.8 | Does the operations and maintenance philosophy in the development phase describe how safety procedures and safe system of works will be applied? |  |  |  | Not Assessed
2.3.9 | Does an operations and maintenance philosophy in the development phase describe how the asset will be integrated into an existing asset management structure? |  |  |  | Not Assessed
2.3.10 | Is the operations and maintenance philosophy produce during the development phase linked to design specifications? |  |  |  | Not Assessed
2.3.11 | Is the operations and maintenance philosophy produced with stakeholders with suitable understanding of operations and maintenance? |  |  |  | Not Assessed
2.4 | Decommissioning
2.4.1 | Is a decommissioning plan produced in the development phase? |  |  |  | Not Assessed
2.4.3 | Does the decommissioning plan record the decommissioning hazards associated with the design concept? |  |  |  | Not Assessed
2.4.4 | Does the decommissioning plan document expected permitting removal requirements in relation to decommissioning? |  |  |  | Not Assessed
2.4.5 | Does the decommissioning plan describe how asset material and components will be recycled? |  |  |  | Not Assessed
2.4.6 | Does the decommissioning plan identify components that can’t be recycled using contemporary technology? |  |  |  | Not Assessed
2.5 | Lessons Learned
2.5.1 | Are lessons learned systematically implemented? |  |  |  | Not Assessed
2.5.2 | Are relevant lessons learned from previous projects considered during the development phase? |  |  |  | Not Assessed
2.5.3 | Are relevant lessons learned from operational sites considered during the development phase? |  |  |  | Not Assessed
2.5.4 | Are relevant lessons learned from the industry considered during the development phase? |  |  |  | Not Assessed
Note on C2: G+: Use the No, Partial, Yes columns when working on a hardcopy
Note on F2: G+: Use this column to set the value and automatically update the 'Summary Dashboard' sheet

## 3. Detailed Design
3. Detailed Design Phase
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
3.1 | Design Basis
3.1.1 | Is a design basis produced that sets out requirements for integrity and applicable legal, regulatory, and statutory requirements? |  |  |  | Not Assessed
3.1.1 | Does the design basis implement approved good practices, and established design practices exist, and/or justify deviations? |  |  |  | Not Assessed
3.2 | Interface Management
3.2.1 | Are there interface management activities that cover the physical asset, the external energy system, contractual responsibilities and projects responsibilities? |  |  |  | Not Assessed
3.2.2 | Is there sufficient resource to effectively manage interfaces? |  |  |  | Not Assessed
3.2.3 | Is there a specific responsibility to manage health and safety considerations in the design process? |  |  |  | Not Assessed
3.2.4 | Are management arrangements put in place where there is the potential for an emergent hazard at contractual interfaces? |  |  |  | Not Assessed
3.3 | Management of Degradation and Deterioration
3.3.1 | Are there activities to avoid or manage degradation that could give rise to hazards? |  |  |  | Not Assessed
3.3.2 | During detailed design are there activities to understand the likelihood and rate of degradation, and its impact on risk levels? |  |  |  | Not Assessed
3.3.3 | During detailed design are there activities to identify deterioration and failure modes that may impact the primary functional requirement and require strategies for through-life management? |  |  |  | Not Assessed
3.3.5 | During detailed design are there activities to evaluate options for the mitigation of deterioration and failures (e.g. as an input to the design of the major asset in terms of resilience, redundancy and maintainability and evaluating prediction and detection methods)? |  |  |  | Not Assessed
3.3.6 | During detailed design are there activities to evaluate risk reduction measures? |  |  |  | Not Assessed
3.3.7 | Where potential degradation has been identified during detailed design is the ability to carry out inspections during the asset life-cycle assessed? |  |  |  | Not Assessed
3.3.8 | During detailed design are there activities to assess the time between detectable degradation and loss of function / catastrophic failure? |  |  |  | Not Assessed
3.4 | Design for Constructability, Operability, Maintainability and Decommissioning
3.4.1 | Is a holistic and whole life perspective taken during detailed design that considers constructability, operability, maintainability and decommissioning? |  |  |  | Not Assessed
3.4.2 | Does the design process address the management of stored energy and safety from the system? |  |  |  | Not Assessed
3.4.3 | Does the design process address isolation requirements, ensuring they can be easily and effectively implemented? |  |  |  | Not Assessed
3.4.4 | Does the design process provide remote operation of switches and points of isolations? |  |  |  | Not Assessed
3.4.5 | Does the design process consider position of anchor points in relation to foreseeable routine and non-routine use cases? |  |  |  | Not Assessed
3.4.6 | Does the design process consider manual and materials handling (from good inwards at the operations and maintenance warehouse, through to the point of work including lifting arrangements) |  |  |  | Not Assessed
3.4.7 | Does the design process consider logistics including personnel access? |  |  |  | Not Assessed
3.4.8 | Does the design process consider complex and non-routine activities? |  |  |  | Not Assessed
3.4.9 | Does the design process consider security requirements? |  |  |  | Not Assessed
3.4.10 | Does the design process consider lifting requirements? |  |  |  | Not Assessed
3.4.11 | Does the design process consider access for maintainability / repairability? |  |  |  | Not Assessed
3.4.12 | Does the design process consider ability to inspect for the degradation mechanisms? |  |  |  | Not Assessed
3.4.13 | Does the design process consider location of any non-inspectable areas? |  |  |  | Not Assessed
3.4.14 | Does the design process address cyber security? |  |  |  | Not Assessed
3.4.15 | Does the design process consider lighting requirements? |  |  |  | Not Assessed
3.4.16 | Does the design process consider site communications? |  |  |  | Not Assessed
3.4.17 | Does the design process consider bunding? |  |  |  | Not Assessed
3.4.18 | Does the design process consider chemicals, gasses, and fuels? |  |  |  | Not Assessed
3.4.19 | Does the design process address the prevention of falls from height and dropped objects? |  |  |  | Not Assessed
3.4.20 | Does the design process consider prevention of slips, trips and falls? |  |  |  | Not Assessed
3.4.21 | Does the design process consider access and egress routes? |  |  |  | Not Assessed
3.4.22 | Does the design process consider fire prevention? |  |  |  | Not Assessed
3.4.23 | Does the design process consider confined spaces? |  |  |  | Not Assessed
3.4.24 | Does the design process consider subsea work and diving? |  |  |  | Not Assessed
3.4.25 | Does the design process consider environmental discharge? |  |  |  | Not Assessed
3.4.26 | Does the design process involve input from a wide range of suitable stakeholders? |  |  |  | Not Assessed
3.4.27 | Are human factors and ergonomics considered through the design process? |  |  |  | Not Assessed
3.4.28 | Does the design process ensure the asset is designed in consideration of foreseeable tasks? |  |  |  | Not Assessed
3.4.29 | Does the design process consider how people can potentially mistakenly impact the safe operation of the asset and appropriate measures taken (e.g. through error-proofing principles and interlocks)? |  |  |  | Not Assessed
3.4.30 | Does the design process consider how safety devices could be defeated and appropriate measures taken? |  |  |  | Not Assessed
3.4.31 | Does the design process consider learnings from operational assets, similar projects and the industry? |  |  |  | Not Assessed
3.4.32 | Is the operations and maintenance philosophy updated during detailed design and further definition added? |  |  |  | Not Assessed
3.4.33 | Is the decommissioning plan updated during detailed design and further definition added? |  |  |  | Not Assessed
3.5 | Design for Escape and Evacuation
3.5.1 | Does the design process consider emergency situations? |  |  |  | Not Assessed
3.5.2 | Does the design process consider the realistic time to enact an emergency plan? |  |  |  | Not Assessed
3.5.3 | Does the design process consider situations where personnel can leave the asset in a planned, managed, and controlled way, without being directly exposed to Hazards? |  |  |  | Not Assessed
3.5.4 | Does the design process consider escapes where there isn’t sufficient time to execute an orderly evacuation? |  |  |  | Not Assessed
3.5.5 | Does the design process consider access and egress arrangements including safe routes of escape and alternative routes, routes in dark or smoke-filled environment, use of markings on floors and emergency lighting? |  |  |  | Not Assessed
3.5.6 | Does the design process consider of position and type of smoke and fire detectors, their sensitivity, how much warning before a situation could escalate? |  |  |  | Not Assessed
3.5.7 | Does the design process consider segregation of people from hazards and safe havens? |  |  |  | Not Assessed
3.5.8 | Does the design process consider the type and positioning of life saving kit, escape shuts, life rafts etc.? |  |  |  | Not Assessed
3.5.9 | Does the design process consider method of communications in emergency such as automatic systems for identifying the locations of people? |  |  |  | Not Assessed
3.5.10 | Does the design process consider the placement of manual alarm raising points? |  |  |  | Not Assessed
3.5.11 | Does the design process consider use of low flammability materials, low smoke, and low toxicity smoke materials? |  |  |  | Not Assessed
3.5.12 | During design is a emergency response and detailed fire management plan produced? |  |  |  | Not Assessed
3.6 | Safety Critical Systems
3.6.1 | Does the design process identify safety critical systems? |  |  |  | Not Assessed
3.6.2 | Does the design process establish performance standards in terms of functionality, reliability, availability and survivability? |  |  |  | Not Assessed
3.6.3 | Does the design process establish interactions and dependencies of safety critical systems? |  |  |  | Not Assessed
3.6.4 | Does the design process define appropriate inspection and maintenance strategies for safety critical systems? |  |  |  | Not Assessed
3.6.5 | Does the design process establish settings for alarms and trip setting, and identify how close these are to failure points? |  |  |  | Not Assessed
3.6.6 | During design are measurable and auditable performance standards established? |  |  |  | Not Assessed
3.7 | Design Freeze and Design Change Management
3.7.1 | During design is there a planned design freeze process where the design is documented and design change management is introduced? |  |  |  | Not Assessed
3.7.2 | At the point of design freeze are hazards and implemented risk reduction measures, design drawings and documentation, residual risks and 'open' design decisions recorded? |  |  |  | Not Assessed
3.7.3 | Following design freeze, if there a change management process that includes review and approval to change and the use to a deign change log? |  |  |  | Not Assessed
3.7.4 | Following design freeze does the change management process specifically consider any changes to isolation points? |  |  |  | Not Assessed
3.7.5 | Following design freeze does the change management process specifically consider any changes to hazards and previous risk assessments? |  |  |  | Not Assessed
3.7.6 | Following design freeze does the change management process specifically consider any changes to design assumptions? |  |  |  | Not Assessed
3.7.7 | Following design freeze does the change management process specifically consider how changes will impact the operations and maintenance philosophy? |  |  |  | Not Assessed
3.7.8 | Following design freeze does the change management process specifically consider how changes will impact the emergency plan? |  |  |  | Not Assessed
3.7.9 | Following design freeze does the change management process specifically consider how changes will impact the material handling plan? |  |  |  | Not Assessed
3.7.10 | Following design freeze does the change management process specifically consider how changes will impact the decommissioning plan? |  |  |  | Not Assessed
3.8 | Design Reviews
3.8.1 | Does the project plan include a programme of meaningful design reviews? |  |  |  | Not Assessed
3.8.2 | Do design reviews include input from operational and health and safety specialists? |  |  |  | Not Assessed
3.8.3 | Is the satisfactory completion of the activities required to manage health and safety risks part of formal design reviews? |  |  |  | Not Assessed
3.9 | Design Verification and Design Assurance
3.9.1 | Does the design process include appropriate design verification and design assurance activities? |  |  |  | Not Assessed
3.9.2 | Does the design process check compliance with standards and codes? |  |  |  | Not Assessed
3.9.3 | Does the design process ensure that the design satisfies the health and safety objectives? |  |  |  | Not Assessed
3.9.4 | Does the design process ensure that there is consideration of constructability, operability, maintainability and decommissioning? |  |  |  | Not Assessed
3.9.5 | Does the design process ensure that residual risks are acceptable? |  |  |  | Not Assessed
3.9.6 | Does the design process ensure that risk reduction measures have been effectively implemented? |  |  |  | Not Assessed
3.9.7 | Does the design verification include individuals who are independent from the project? |  |  |  | Not Assessed
Note on C2: G+: Use the No, Partial, Yes columns when working on a hardcopy
Note on F2: G+: Use this column to set the value and automatically update the 'Summary Dashboard' sheet

## 4. Construction
4. Construction Phase
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
4.1 | Work Scheduling
4.1.1 | Is the sequencing and scheduling of work considered with the objective of minimising the risks associated with simultaneous activities? |  |  |  | Not Assessed
4.1.2 | Is there a plan for the application of safety rules through the build and commissioning phases, including when different rules will be applied and the authorisation process? |  |  |  | Not Assessed
4.1.3 | Is there a plan to manage the energisation process with appropriate assurance and authorisation? |  |  |  | Not Assessed
4.2 | Management of Temporary Works
4.2.1 | Is the management of temporary works subject to the same principles set out for the permanent asset? |  |  |  | Not Assessed
4.2.2 | Where temporary works interact with the permanent asset are the additional loads considered and how these relate to the design load cases and their impact on the short and long-term life? |  |  |  | Not Assessed
4.2.3 | Where there is a non-negligible impact is analysis carried out with a suitable approval required before commencement? |  |  |  | Not Assessed
4.3 | Quality Management
4.3.1 | Is there a risk-based quality plan that considers the identified Hazards and complexity and risks of managing issues in the construction, operation and/or decommissioning? |  |  |  | Not Assessed
4.3.3 | When assessing concession proposals and non-conformities is the impact on hazards, and likelihood of future non-routine and complex rectification work, considered? |  |  |  | Not Assessed
4.3.4 | Is the justification of accepting deviations documented and does this form part of the asset information? |  |  |  | Not Assessed
4.3.5 | During construction are quality checks undertaken on critical areas that are exposed to degradation and cannot be inspected during operational life? |  |  |  | Not Assessed
4.3.6 | During construction are quality checks include the measurements of any health and safety critical parameters? |  |  |  | Not Assessed
4.3.7 | Does the quality plan specifically and demonstrably cover activities to ensure safety related systems are installed and commissioned as intended and they comply with the performance requirements? |  |  |  | Not Assessed
4.4 | Design Change
4.4.1 | Does the design Change Management process continue during the construction phase with the same approval process for justifying change? |  |  |  | Not Assessed
4.5 | Capturing Lessons Learned
4.5.1 | Is there a lessons learned register that records where the hazards during construction could have been reduced with alternative design decisions? |  |  |  | Not Assessed
Note on C2: G+: Use the No, Partial, Yes columns when working on a hardcopy
Note on F2: G+: Use this column to set the value and automatically update the 'Summary Dashboard' sheet

## 5. Asset Adoption
5. Asset Adoption
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
5.1 | Handover
5.1.1 | Is there a specific handover plan to adopt and transfer the asset into operations? |  |  |  | Not Assessed
5.1.2 | Does the handover plan include recording and transfer of asset information? |  |  |  | Not Assessed
5.1.3 | Does the handover plan include communication of key risks (and where they may manifest)? |  |  |  | Not Assessed
5.1.4 | Does the handover plan include the provision of design information? |  |  |  | Not Assessed
5.1.5 | Does the handover plan include information regarding degradation mechanisms? |  |  |  | Not Assessed
5.1.6 | Does the handover plan include design assumptions? |  |  |  | Not Assessed
5.1.7 | Does the handover plan include unresolved non-conformities? |  |  |  | Not Assessed
5.1.8 | Does the handover plan include establishment of safe system of work processes? |  |  |  | Not Assessed
5.1.9 | Does the handover plan include emergency response plan? |  |  |  | Not Assessed
5.1.10 | Does the handover plan include competency requirements? |  |  |  | Not Assessed
5.1.11 | Does the handover plan include any snags / punch list items with a plan for rectification? |  |  |  | Not Assessed
5.1.12 | Does the handover plan include an alarm management plan identifying which alarms can be reset, those that need further investigation and protocols? |  |  |  | Not Assessed
5.1.13 | Does the handover plan include asset register? |  |  |  | Not Assessed
5.1.14 | Does the handover plan include residual risks? |  |  |  | Not Assessed
5.1.15 | Is the handover plan agreed between senior representatives from the construction and operations departments? |  |  |  | Not Assessed
5.1.16 | Does the handover plan clearly describe the transfer of responsibilities and the timeline? |  |  |  | Not Assessed
5.1.17 | Is the handover plan subject to regular reviews between the relevant stakeholders? |  |  |  | Not Assessed
5.2 | Conversation of Design Information into Operations Documents
5.2.1 | Is the documentation necessary to manage the asset in accordance with the health and safety objectives produced and accessible? |  |  |  | Not Assessed
5.2.2 | Are maintenance manuals provided to the operations department? |  |  |  | Not Assessed
5.2.3 | Is the maintenance scope and frequencies provided to the operations department? |  |  |  | Not Assessed
5.2.4 | Are inspection criteria (i.e. acceptance levels) provided to the operations department? |  |  |  | Not Assessed
5.2.5 | Is the inspection scope and frequencies provided to the operations department? |  |  |  | Not Assessed
5.2.6 | Are expected degradation rates provided to the operations department? |  |  |  | Not Assessed
5.2.7 | Are isolation procedures provided to the operations department? |  |  |  | Not Assessed
Note on C2: G+: Use the No, Partial, Yes column when working on a hard copy
Note on F2: G+: Use this column to set the value and automatically update the 'Summary Dashboard' sheet

## 6. Operations
6. Operations
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
6.1 | Design Validation
6.1.1 | Is there a plan that includes activities to validate the design assumptions? |  |  |  | Not Assessed
6.1.2 | Are there activities to assess degradation rates and performance of any parts of the design intended to control degradation? |  |  |  | Not Assessed
6.1.3 | Are there activities to assess the magnitude and frequency of the applied loads and compare with design assumptions? |  |  |  | Not Assessed
6.1.4 | Are there activities to assess environmental conditions and compare these with design assumptions? |  |  |  | Not Assessed
6.1.5 | Are any differences between design assumptions and observations reviewed and assessed to understand the significance and where appropriate, mitigation actions implemented? |  |  |  | Not Assessed
6.2 | Maintaining H&S objectives
6.2.1 | Is there a plan to maintain health and safety objectives in the operational phase? |  |  |  | Not Assessed
6.2.2 | Is Good Industry Practice monitored and action taken when there are improvements in risk management practices? |  |  |  | Not Assessed
6.2.3 | Are risk assessments regularly reviewed and where necessary updated? |  |  |  | Not Assessed
6.2.4 | Are external factors reviewed and, where there is a change, their impact on hazards and risk profile assessed and where necessary risk reduction measured updated? |  |  |  | Not Assessed
6.3 | Emergency Response
6.3.1 | Is there a process to regularly review the emergency response plan? |  |  |  | Not Assessed
6.3.2 | Are emergency response trials carried out to assess their effectiveness? |  |  |  | Not Assessed
6.3.3 | Is the time required to enact an emergency response plan assessed and compared with the speed a hazard may escalate? |  |  |  | Not Assessed
6.4 | Inspection, Maintenance and Monitoring
6.4.1 | Are there processes for planning, executing, and recording appropriate inspection and maintenance? |  |  |  | Not Assessed
6.4.2 | Are the asset care requirements reviewed and updated as the asset ages? |  |  |  | Not Assessed
6.4.3 | Are the technicians provided with information of any asset features that may be unique to the site and require special attention in relation to safety? |  |  |  | Not Assessed
6.4.4 | Is the management of temporary works subject to the same principles set out for the permanent asset? |  |  |  | Not Assessed
6.4.5 | Where temporary works interact with the permanent asset are the additional loads considered and how these relate to the design load cases and their impact on the short and long-term life? |  |  |  | Not Assessed
6.4.6 | Where there is a non-negligible impact is analysis carried out with a suitable approval required before commencement? |  |  |  | Not Assessed
6.4.7 | Are events that put loads through the system that are outside the design basis, or cause significant damage assessed prior to returning the asset to service? |  |  |  | Not Assessed
6.4.8 | Is the activation of safety related systems monitored and investigations undertaken where the 'last line of defence' system is deployed? |  |  |  | Not Assessed
6.4.9 | Is there a process for managing any deterioration in the performance levels of safety related systems? |  |  |  | Not Assessed
6.5 | Asset Modifications and Brownfield projects
6.5.1 | Is there a process for managing modifications to the asset? |  |  |  | Not Assessed
6.5.2 | Does the process include authority levels required to approve changes, the documentation requirements, and the requirements for risk assessment? |  |  |  | Not Assessed
6.5.3 | Does the process include a consideration of the points of isolation, existing practices, competency requirements? |  |  |  | Not Assessed
6.5.4 | Are software changes, changes to maintenance regimes, temporary changes, and alarm changes (particularly where critical) subject to an appropriate change management process? |  |  |  | Not Assessed
6.5.5 | When complex brownfield projects are required is the competency of the operations team considered and suitable construction support provided? |  |  |  | Not Assessed
6.6 | Capturing Operational Experience
6.6.1 | Is operational experience relating to health and safety captured, suitably arranged, and made available to team designing new Projects? |  |  |  | Not Assessed
6.6.2 | Are incidents that include design as a cause identified, investigated, and fed back into new projects? |  |  |  | Not Assessed
6.7 | Life Extension
6.7.1 | Is transition into a life extension subject to a change management plan? |  |  |  | Not Assessed
6.7.2 | Is a life-extension approval process require an understanding of time degradation mechanisms? |  |  |  | Not Assessed
6.7.3 | Is there a specific integrity management plan developed and implemented to manage the increased risks presented by going beyond the design life? |  |  |  | Not Assessed
6.8 | Decommissioning Plan Review
6.8.1 | Is the decommissioning plan regularly reviewed? |  |  |  | Not Assessed
6.8.2 | Is specific consideration given to any changes or improvements in relevant Good Industry Practice since previous iterations? |  |  |  | Not Assessed
6.8.3 | Are the implications of changes in asset condition and integrity considered when planning decommissioning? |  |  |  | Not Assessed
6.8.4 | Are there activities to review the expected decommissioning methodology and identify opportunities to reduce risks (for example through the development of new technology) and resources put into realising the potential benefits? |  |  |  | Not Assessed
Note on C2: G+: Use this No, Partial, Yes column when working on a hard copy
Note on F2: G+: Use this column to set the value and automatically update the 'Summary Dashboard' sheet

## 7. Decomissioning
7. Decommissioning
Item | Question | No | Partial | Yes | Status | Supporting comments | Actions | Owner | Date
7.1 | Planning
7.1.1 | Does planning for decommissioning start well in advance of the end of the useful life of the asset? |  |  |  | Not Assessed
7.1.2 | Is the decommissioning plan regularly reviewed and updated? |  |  |  | Not Assessed
7.1.3 | Is the supply chain and other stakeholders involved in decommissioning planning? |  |  |  | Not Assessed
7.1.4 | Are hazard identification and risk reduction principles used? |  |  |  | Not Assessed
7.1.5 | Is the relevant asset information made available to the decommissioning team? |  |  |  | Not Assessed
7.1.6 | Is the management of temporary works subject to the same principles set out for the permanent asset? |  |  |  | Not Assessed
7.2 | Degradation Assessment
7.2.1 | Is the level of asset degradation assessed and fed back into the new designs? |  |  |  | Not Assessed
7.2.2 | Is a plan produced to identify any areas of the asset considered suitable for investigation to support new designs and the operational management of other assets? |  |  |  | Not Assessed
Note on C2: G+: Use the No, Partial, Yes columns when working on a hardcopy
Note on F2: G+: Use this column to set the value and automatically update the 'Summary Dashboard' sheet